## MRS
HAMPEDevs
| Group | 1 |  |  | DEPARTMENT |  |  |  | Computer Engineering | [7 empty] | STATUS COLOR
| SEMESTER | 2nd Semester |  |  | SY |  |  |  | 2025-2026 | [10 empty] | Not yet Done |  |  | In Progress |  |  | Done
ID | TASK | START DATE | DUE DATE | STATUS | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18
 | time axis 2025-11-29 to 2026-04-03
1 | Planning Phase
1.1 | Brainstorming | 11/29/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
1.2 | Researching | 11/29/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
1.3 | Progress 1, 2, 3 | 11/29/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
1.4 | Progress 4, 5, 6 | 12/13/2025 | 12/20/2025 | In Progress | 2025-12-21: Vacation
1.5 | Progress 7, 8 | 01/24/2026 | 12/06/2025 | In Progress | 2025-12-21: Vacation
1.6 | Conceptualization | 11/29/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
1.7 | Searching for possible client | 11/29/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
1.8 | Background checking of the possible client | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
1.9 |  | 12/13/2025 | 12/20/2025
2 | Requirements
2.1 | Letters for Client Meeting | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.2 | Letter of Intent | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.3 | Budget Proposal | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.4 | Figma Design | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.5 | Project Proposal | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.6 | Abstract for Client | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.7 | Meeting for Client | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
2.8 | Analyzing and interpreting the data | 11/30/2025 | 12/06/2025 | Done | 2025-12-21: Vacation
3 | Design Phase
3.1 | Algorithm | 01/24/2026 | 02/14/2025 | In Progress | 2025-12-21: Vacation
3.2 | Flowchart | 01/24/2026 | 02/14/2025 | In Progress | 2025-12-21: Vacation
3.3 | DFD (Data Flow Diagram) | 01/24/2026 | 02/14/2025 | In Progress | 2025-12-21: Vacation
3.4 | ERD (Entrity-Relationship Diagram) | 01/24/2026 | 02/14/2025 | In Progress | 2025-12-21: Vacation
3.5 | Storyboarding | 01/24/2026 | 02/14/2025 | In Progress | 2025-12-21: Vacation
4 | Development Phase
4.1 | FIGMA UI/UX Design User Interface | 12/06/2025 | 01/14/2026 | Done | 2025-12-21: Vacation
4.2 | HTML and CSS Coding Front End | 01/14/2026 | 02/14/2026 | In Progress | 2025-12-21: Vacation
4.3 | C++ and MySQL Coding Back End | 01/14/2026 | 01/14/2026 | In Progress | 2025-12-21: Vacation
4.4 | System Testing |  |  |  | 2025-12-21: Vacation
4.5 | Debugging |  |  |  | 2025-12-21: Vacation
5 | QA & Testing
5.1 | Multiple Device Test |  |  |  | 2025-12-21: Vacation
5.2 | Beta Testing |  |  |  | 2025-12-21: Vacation
6 | Deployment & Maintenance
6.1 | Authoring Privacy Policies and User Manual |  |  |  | 2025-12-21: Vacation
6.2 | Deployment |  |  |  | 2025-12-21: Vacation
6.3 | Maintenance |  |  |  | 2025-12-21: Vacation
7 | Documentation
7.1 | Chapter 1: Introduction | 01/10/2026 |  | Done | 2025-12-21: Vacation
7.2 | Chapter 2: Review of Related Literature and Studies | 01/10/2026 |  | Done | 2025-12-21: Vacation
7.3 | Chapter 3: Methodology | 01/17/2026 |  | In Progress | 2025-12-21: Vacation
7.4 | Chapter 4: Results and Discussion |  |  |  | 2025-12-21: Vacation
7.5 | Chapter 5: Conclusion |  |  |  | 2025-12-21: Vacation
7.6 | Final Paper Check |  |  |  | 2025-12-21: Vacation
7.7 | Defense |  |  |  | 2025-12-21: Vacation